## RAID
No. | Category | Description | Priority | Owner | Next Actions
1 | Risk | Low adoption of mobile app chatbot due to user preference for existing support channels | Medium | Product + Marketing | Define target segments and launch channels; run A/B test on onboarding flows and messaging; track adoption funnel (view → engage → resolve)
2 | Risk | Non-compliance with data privacy and regulatory requirements (e.g., GDPR, financial data handling) | Critical | Legal + Compliance + Product | Define data usage policies; conduct privacy impact assessment; align on data storage, consent, and audit requirements before build
3 | Risk | Mobile app defects or instability degrade user experience and reduce trust in the product | Low | Engineering + QA | Define QA strategy; implement automated and regression testing; establish monitoring and incident response plan pre-launch
4 | Risk | Insufficient service rep training and change management limit effective adoption and support alignment | Medium | Product + CX Operations | Develop training materials and playbooks; run pilot training sessions; gather feedback and iterate before full rollout
5 | Risk | Increased user volume leads to latency or slow response times, negatively impacting experience | Medium | Engineering + Infrastructure | Conduct load and stress testing; define SLAs for response times; implement scalability plan (auto-scaling, queuing)
6 | Risk | API failures or integration issues disrupt chatbot functionality and data flow | Medium | Engineering + Platform Teams | Validate API contracts; implement fallback/error handling; conduct end-to-end integration testing across systems
7 | Risk | Low user trust in AI-driven support limits engagement and usage | High | Product + UX Research | Conduct user interviews and surveys; test messaging and transparency features (e.g., “human escalation”); iterate based on feedback
8 | Risk | User preference for human interaction reduces willingness to engage with chatbot solutions | High | Product + UX Research | Test hybrid support flows (chatbot + human handoff); measure engagement vs escalation rates; refine experience to balance automation and human touch
9 | Risk | Chatbot delivers inaccurate, incomplete, or inefficient resolutions, increasing frustration | Medium | Engineering + Data Science | Define accuracy benchmarks; train and validate models using historical data; implement feedback loop for continuous improvement
10 | Risk | Product fails to meaningfully reduce churn despite adoption and usage | High | Product + Analytics | Define success metrics and baseline churn; run controlled A/B test; analyze impact and identify gaps in experience or targeting
11 | Assumption | Churn is primarily driven by call center inefficiencies rather than individual service rep performance | High | Product + Analytics | Validate via call transcript analysis and customer feedback; segment churn drivers; confirm root cause before scaling solution
12 | Assumption | Product quality is not the primary driver of churn based on current analysis | Low | Product + Analytics | Validate through surveys and product feedback data; monitor for conflicting signals post-launch
13 | Assumption | Customers are willing to shift from human-assisted support to chatbot-based self-service | High | Product + UX Research | Test willingness via pilot launch and A/B testing; measure adoption and satisfaction across segments
14 | Dependency | API framework is available and supports reliable, scalable integrations | Low | Engineering + Platform Teams | Confirm API readiness and SLAs; identify gaps; align integration timeline with product roadmap
15 | Dependency | CRM data platform is accessible and provides accurate, up-to-date customer data | Medium | Data Engineering + Analytics | Audit data quality and availability; define data requirements; implement data validation checks
16 | Dependency | Invoicing data platform is accessible and provides accurate transaction and billing data | Medium | Data Engineering + Analytics | Validate data completeness and accuracy; ensure integration supports required use cases
17 | Dependency | Ticketing data platform is accessible and provides complete and reliable support interaction data | Medium | Data Engineering + CX Systems | Confirm data capture and structure; align taxonomy for issue tracking and analysis
18 | Dependency | ML/AI models and analytics infrastructure are available to power chatbot intelligence and insights | High | Data Science + Engineering | Conduct capability assessment; define model requirements; align on build vs buy and budget needs
19 | Dependency | Mobile app supports seamless chatbot integration and user experience | High | Engineering + Product + UX | Define integration requirements; design user flows; validate experience through usability testing before release