## Roadmap
Vision:
Deliver a seamless, personalized customer service experience through an intelligent in-app messaging platform that unifies customer interactions, transaction data, and service insights.
Strategic Goals: | KPIs
Enhance Customer Satisfaction | Churn, CLV
Increase Mobile App Engagement | Usage Rate
Deepen Customer Insights | Usage Rate; Prediction Success Rates from analytics
Theme
Mobile Chat Capability
Data & Systems Integration
Service Excellence Enablement
Adoption & Engagement
Insights & Intelligence
Theme | Feature | Start | End
Data & Systems Integration | Customer Data Integration (CRM) | Q4 2026 | Q1 2027
| Transaction & Billing Integration (Invoicing) | Q4 2026 | Q1 2027
| Support Workflow Integration (Ticketing) | Q1 2027 | Q2 2027
| Unified Data Layer Development | Q4 2026 | Q2 2027
| Integration Validation & Monitoring | Q1 2027 | Q2 2027
Mobile Chat Capability | Chat Experience Design | Q4 2026 | Q1 2027
| In-App Messaging Platform Development | Q1 2027 | Q2 2027
| Quality Assurance & Release Readiness | Q2 2027 | Q2 2027
Insights & Intelligence | Analytics Data Model Development | Q1 2027 | Q2 2027
| Service & Customer Insights Dashboard | Q2 2027 | Q2 2027
| Insights Platform Development | Q2 2027 | Q3 2027
| Performance Measurement Framework | Q1 2027 | Q2 2027
| Data Quality & Validation | Q2 2027 | Q3 2027
Service Excellence Enablement | Service Rep Training & Onboarding | Q2 2027 | Q3 2027
| Chat Support Playbooks & Workflows | Q2 2027 | Q2 2027
| Insights & Tooling Enablement | Q3 2027 | Q3 2027
Adoption & Engagement | Go-to-Market Strategy & Campaign Planning | Q2 2027 | Q3 2027
| In-App Feature Promotion & User Education | Q2 2027 | Q3 2027
| Launch & Adoption Optimization | Q3 2027 | Q4 2027

## Prioritization
Theme | Priority | Reach (Users) | Impact | Confidence | Effort (Months) | RICE Score | Dependencies | Notes
Mobile Chat Capability | 1 | 10000 | 3 | 60% | 5 | 3600 | Data integration (partial) | Core feature driving CX + churn reduction
Data & Systems Integration | 2 | 10000 | 2 | 75% | 9 | 1666.6667 | None (foundational) | Enables all downstream capabilities
Service Excellence Enablement | 3 | 10000 | 3 | 85% | 2 | 12750 | Chat capability | Improves service outcomes + reduces churn
Adoption & Engagement | 4 | 15000 | 1 | 60% | 2 | 4500 | Chat capability | Expands usage + ROI
Insights & Intelligence | 5 | 250 | 2 | 80% | 4 | 100 | Data + chat data | Internal decision support